## Sheet1
TP ID | TP Name | Protocol | Stage | Assigned To | Started | Target Go-Live | Notes
TP009 | Omega Logistics | SFTP | Testing | Aditya K. | 2026-03-01 | 2026-03-10 | SSH key exchange pending
TP010 | Delta Retailers | AS2 | In Progress | Ravi M. | 2026-03-03 | 2026-03-12 | Certificate exchange done, configuring MDN
TP011 | Apex Manufacturing | FTPS | Not Started | Priya S. | 2026-03-07 | 2026-03-15 | Waiting for TP SSL cert
TP012 | Nexus Pharma | SFTP | Go-Live | Aditya K. | 2026-02-20 | 2026-03-05 | Go-live delayed — JO approval pending